## MVP - 1 Instance with 1 LFC
|  | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01
Week Commencing | Resource Name | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30
POC on PT script recording for Web Terminal
|  |  | NFR Requirement Gathering** - Dependency on Business (Currently with Kieran) |  |  | PT Scenario identification and workload distribution
Data Analysis (Understanding DB stucture and creating SQL scripts)
|  |  | V&P Env readiness (Infrastucture+ Application code to be deployed)** | [9 empty] | Data Creation in VnP DB(Reference+ Transaction data)
|  | Identifying Server Side KPI Monitoring | [10 empty] | Server Side KPI Monitoring Configuration and finalization in VnP env
[7 empty] | PT Script preparation & validation in Functional Test Env | [5 empty] | PT Script prepared to be validated for VnP env ** (May need rework for scripting and validation)
Individual Functionality PT in Fuctional Testing Env (Testing + Response analysis)
|  |  |  | Integration Test Planning , indentifying the interfaces and scenarios (with LSP and Argos) | [8 empty] | LSP to Koerber Reference Data PT
Transaction Mix Avg & Peak load (Testing+ Result Analysis+Reporting )
Backup and Recovery of data -Planning and execution
Documentation In confluence or Github
Application Optimization and validation (Server side and code level)
Azure Pipeline Setup for PT automation
Endurance , Peak Volume with Reporting-1 Round
Integrated VnP Test witn LSP, Argoes team
Regression Test (Repeated test of Transaction Mix scenario)
Final Report Preparation and Signoff
VnP Lead | Bishnupriya Nanda | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
VnP engineer 1(offshore) | Ajith Arumugam | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
VnP engineer 2 (offshore) | TBC | [6 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Total PD's - Offshore + Onsite
Total WO Cost
Considerations
Tasks | Responsibility
NFR Strategy Preparation | VnP Lead and VnP Engineer
Performance Test Plan | VnP Lead
KPI anlysis | VnP Lead
POC on Testing Tool | VnP Engineer
V&P Env Setup | VnP Lead
Workload Design as per NFR | VnP Lead and VnP Engineer
Performance Script Preparation and Validation | VnP Engineer
Data Analysis and creation | VnP Lead and VnP Engineer
PT Script creation and Validation | VnP Engineer
Individula Functionality PT | VnP Engineer
Transaction Mix PT | VnP Engineer
Data Backup and Recovery | VnP Lead and VnP Engineer
PT with Integration Team | VnP Lead and VnP Engineer
Azure Pipeline setup for automated PT | VnP Lead and VnP Engineer
Endurance and Failover Test | VnP Engineer
Application Tuning and Validation | VnP Lead and VnP Engineer
Regression Testing | VnP Engineer
Result analysis and signoff | VnP Lead
Assumption
Risks
-If there is delay in getting NFR and VnP env . The plan to complete V&P by May 30th may impact.50:51

## Options
Options | Description
Option 1 | 1. Identification of Interfaces between Argos applications E.g. Sterling, Aura) to LSP and from LSP 2. Koerber VnP environment is not required for this testing (Koerber PT environment will be ready by 15th March 2022) 3.Check with Sanjay/Deepak/Gouwri/Abdul for Argos side PT environment readiness 4. Check with Vinay and Madhab for LSP side PT environment readiness. 5. If point number 1,3 and 4 is available , the interfaces in scope as per point-1 and we have NFR confirmed, this PT testing can be planned. 6. This PT testing main ownership will be with Argos PT team(Deepak/Sanjay) along with Vinay Note: Meeting is planned to discuss on W/C 18th Jan 2022 and note all the key points a.NFR b. PT Test scope c. PT test scripts d. PT test data e. PT test environment
Option 2 | Use functional test env (Functional testing will move to new env). What all activities can be possible. 1.Koerber PT Scripting can be started 2. Invidual Koerber functionality performance can be validated. Risk and Challenges 1. Heavy production like volume cannt be created in less config env. 2.Rework for existing Koerber PT script. 3. Individual Functionality response can varriy in VnP env from functional Testing env. 4. Cannt finalize server metrics in functional env as the VnP will be different (e.g. LB is not present in funtional env and configuration is less) 5. Integration testing with Argos to LSP and Koerber and viceversa cannt be done.
Option 3 | VnP environment can only be available from Mar 15th. 1. Shifting the plan 2. Risk of missing the timeline/ excluding some activities

## Activities
Activities | Description | Responsibility | Dependency | Status | Comments
POC on PT script recording for Web Terminal | To verify Jmeter tool is able to capture the all the request of this applciatioin | VnP Testing Team (Bishnu/Ajith) |  | Completed
Koerber NFR Requirement Gathering** | 1. Peak & averge concurrent users for both Koerber One UI and RF device 2. End to End response time or tps SLA 3. Critical and frequent scenriaos 4. Server Utilization SLA (e.g. CPU <60% and Memory <60%) 5. Transactional Data volume above which to carry out the load test. 6.VnP team to understand and finalize with application team | Product/Application Team/VnP Testing Team(Bishnu) | Business or product owner | In progress | Discussed with Kieran and concluded some nos to start with, untill we have the concrete requirement from product team.
PT Scenario identification and workload distribution | 1. To disturbute the user load equally among the identified scenarios as per the criticality 2. Calculating the concurrent users for the given TPS 3. Identifying the scenarios which can be triggered parallel and which are required to be sequencial. 4. Others think time/delay etc. | VnP Testing Team (Bishnu/Ajith/VnP tester 3) | NFR Requirement | Completed
Data Analysis (Understanding DB stucture and creating SQL scripts) | 1. Understanding the master data/reference data and the flow from LSP to Koerber 2. Understanding the transactional data for Inbound /outbound /invetory management. 3. POC on creating script or store procedure to populate huge data in the VnP database | VnP Testing Team (Bishnu/Ajith) |  | In Progress | Understanding of DB structure is done. But data prepartion need to plan.
V&P Env readiness (Infrastucture+ Application code to be deployed) | Production like environment to be created and latest code to be deployed | Cloud Infra Team(Rhys/Anish) |  | In Progress
Data Creation in VnP DB(Reference+ Transaction data) | Need to create a bulk data(Production like volume) in VnP DB eitheir via script or by any other tool | VnP Testing Team (Bishnu/Ajith) | VnP Environment readiness | Not Started
Identifying Server Side KPI Monitoring | Identifying the server side metrics i.e. CPU, memory , disk utilization etc., for all the servers involved | VnP Testing Team(Bishnu) |  | Completed
Server Side KPI Monitoring Configuration and finalization in VnP env | Finalizing the KPIs and enabling the Azure Metrics /insights in VnP env for the identified KPIs. | VnP Testing Team(Bishnu) | VnP Environment readiness | Not Started | Need to finalize whether to go for Data dog or Broadcom (Brodcom is decided for Production monitoring)
PT Script preparation & validation | Creating the scripts for idenified scenarios and validating with single user load with Test data (i.e.Parameterization and correlation). Will start the Scripting and validation in Functional Test env but rework will be needed once VnP env is ready. | VnP Testing Team(Ajith/Tester 3) | Jmeter POC for Web Terninal UI | In Progress | Jmeter POC done. Scripting in progress in Functional Testing env.
Integration Test Planning , indentifying the interfaces and scenarios (with LSP and Argos) | PT planning for interfaces like, Create/Modify Order, Iem/Vendor/location data flow from Sterling to Koerber. Volume of message flow at a time etc. | LSP(Vinay) & Argos VnP team (Sanjoy & Deepak) | LSP & Argos team | In Progress | Identified the scenarios. Order Import 10k is progress in functional testing env.
LSP to Koerber Reference Data PT | How much time its taking for Reference data population from LSP to Koerber . | LSP(Vinay) & Argos VnP team (Sanjoy & Deepak) | LSP and Koerber VnP env readiness. | Not Started
Individual Functionality PT (Testing + Response analysis) | Individual scenarions to be tested and monitor the KPI's responses. Will start the Individual PT in Functional Test Env but rework will be needed once VnP env is ready. | VnP Testing Team(Ajith/Tester 3) |  | In progress | In functional testing env. Bug -KSC-5483, 3564
Transaction Mix Avg & Peak load (Testing+ Result Analysis+Reporting ) | All scenarios to be loaded at a time with Peak and avg user concurrency and reporting the result. | VnP Testing Team(Bishnu/Ajith/Tester 3) | VnP Environment readiness | Not Started
Backup and Recovery of data -Planning and execution | How to take the back of data rolled backed in case of error in execution. If DB size increases that the required volume need to think about the archival process if needed. | VnP Testing Team(Bishnu) | VnP Environment readiness | Not Started
Documentation in Confluence or Github | Placing the developed scripts, aproach and test data in confluence and Git HUB. | VnP Testing Team(Bishnu/Ajith/Tester 3) |  | In progress
Application Optimization and validation (Server side and code level) | Code level changes like method tunning or DB connection pool/Data source tuning , memory leak analysis. Ap/Web/DB server side configuratin optimization if needed. | Application Development Team(Sasank)/VnP testing team (Bishnu/Ajith/Tester 3) | VnP Environment readiness | Not Started
Azure Pipeline Setup for PT automation | Azure pipeline setup -JMeter Scripts and test data placed in GIT Hub repository will be picked and executed through the Jmeter placed in Azure VM (Need to create the Azure Pipeline job). | VnP Testing Team(Bishnu/Ajith) | VnP env readiness and GIT hub access | Completed | Tested for the testing env
Other test ( Endurance , Peak Volume and Failover test with Reporting ) | 1. Test to check the memory leak, high availability and scalability of the application. 2. For Failover we have to swich off one app server and we will monitor all the traffics are going to pne and can be handled by one. | VnP Testing Team(Bishnu/Ajith/Tester 3) | VnP Environment readiness | Not Started
Integrated VnP with LSP, Argos team | Integration testing of the whole end to end from Argoes to LSP to Koerber and Viceversa with requiried volume mentioned in NFR and monitoring all the systems involved. | Koerber, LSP & Argos VnP team(Bishnu/Sanjoy/Deepak/Vinay) | All the three system end to end env is ready and NFR is finalized. | Not Started
Regression Test | Three repeated PT of Transaction mix scnario for Koerber LFC till the application meets the SLA. | VnP Testing Team (Ajith/Tester 3) | After Transaction Mix PT on Avg and Peak load | Not Started
Final Reporting and Signoff | Final result (One report including all test results) analysis and report prepartion with Server side KPIs. | VnP Testing Team (Bishnu) |  | Not Started